AI FAQ Assistant API – Smart FAQ Management powered by Google Gemini AI

Project Planning Phase

# Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

| # DATE | # 25/09/2026 |
| --- | --- |
| # TEAM ID | # SWTID-2026-4431 |
| # PROJECT NAME | # AI FAQ Assistant API |

Team Leader     :       [NITHYA .  P]

Team Members:       [DEEPA  SRI . G],

[MONISHA . S],

[VAITHEESWARI .V],

## Product Backlog & Sprint Schedule

| Sprint | Functional Requirement (Epic) | User Story | Story Points | Priority |
| --- | --- | --- | --- | --- |
| Sprint 1 | Project Setup | As a developer, I can scaffold the Express app, connect MongoDB, and load env config | 3 | High |
| Sprint 1 | Authentication | As a user, I can register and log in and receive a JWT | 5 | High |
| Sprint 1 | Authentication | As a user, I can view my own profile via a protected route | 2 | Medium |
| Sprint 2 | FAQ Management | As a user, I can create, update, and delete my own FAQs | 5 | High |
| Sprint 2 | FAQ Management | As a visitor, I can view all FAQs or one FAQ by ID | 3 | High |
| Sprint 2 | FAQ Management | As a visitor, I can search FAQs by keyword | 3 | Medium |
| Sprint 3 | Validation & Errors | As a developer, I want centralized validation and error handling for consistent API responses | 5 | High |
| Sprint 3 | AI Integration | As a user, I can ask the AI a direct question and get an answer | 5 | High |
| Sprint 4 | AI Integration | As a user, I can give the AI a topic and receive a structured FAQ pair | 5 | High |
| Sprint 4 | Testing & Docs | As a team, we want a Postman collection and README covering every endpoint | 3 | Medium |

## Project Tracker, Velocity & Burndown Summary

The team maintained a consistent velocity of approximately 10 story points per sprint across four sprints, completing all planned backlog items on schedule. Sprint 1 established the foundation (setup + auth); Sprint 2 delivered core FAQ CRUD and search; Sprint 3 added validation, centralized error handling, and the first Gemini endpoint; Sprint 4 completed the AI FAQ generator plus the Postman collection and documentation.

| Sprint | Planned Points | Completed Points | Status |
| --- | --- | --- | --- |
| Sprint 1 | 10 | 10 | Completed |
| Sprint 2 | 11 | 11 | Completed |
| Sprint 3 | 10 | 10 | Completed |
| Sprint 4 | 8 | 8 | Completed |